## Welcome
©2005 Seref, Ahuja, Winston
The critical path method is a quantitative technique to manage projects. This technique models a project as consisting of several activities. Each activity has an associated activity time which denotes the length of the time needed to complete the activity. Activities also have precedence relationships between them, that is, an activity can be started only when some other activities are completed.
There are two options in this application:
1. Find the critical path (CPM)
2. Solve the Time-Cost Tradeoff problem
For the CPM option:
Given the data about activities, this application computes the Early Start Time (the earliest time the activity can start) and Late Start Time (the latest time the activity can start) of each activity. From these times, Free Float and Total Float for each activity are computed. Any activity with a Total Float of zero is on a critical path.
For the Time-Cost Tradeoff option:
The user also provides crash times and crash costs for each activity. A linear programming model is solved to find the best selection of activities which should be crashed to minimize the total project cost.
For more details on the critical path method, please see "Introduction to Operations Research" by Winston.
The Critical Path Method
Start Program
Run Demo

## Network Sheet (hidden)
Apply the critical path method to your own example. Please follow the steps given below to specify your example. To see an example of the format, click on See Example. | (Help?)
Use the drawing objects to create your own network:
A. For the CPM option, create your network such that each NODE = EVENT and each ARC = ACTIVITY. You will also need to name the arcs in order to see your resulting critical path (see the Help comments).
B. For the Time-Cost Tradeoff optoin, create your network such that each NODE = ACTIVITY.
Click Continue to fill in the Activity Table and the Precedence Matrix.
1
1
Continue
End
Return to Report
See Example
Network
Return to Activity Table
Return to Precedence Matrix
1
5
6
7
4
3
2
t
s
Note on H3: 1. Copy and paste the node and arc shapes on the right of this box to create your network. 2. Define a NAME property for each arc using the Name Window in the top left corner of your screen (or Insert < Name < Define menu options). The arc names should be defined as "Activity1", Activity2", etc. 3. After naming each arc, label arcs by their activity times by using the text box provided.

## Activity Sheet (hidden)
Activity Name | Description | Normal Duration | Normal Cost | Crash Duration | Crash Cost
1 | Activity 1 | 6 | 100 | 4 | 240
2 | Activity 2 | 2 | 100 | 1 | 150
3 | Activity 3 | 3 | 30 | 3 | 30
4 | Activity 4 | 2 | 30 | 2 | 30
5 | Activity 5 | 4 | 100 | 2 | 180
6 | Activity 6 | 1 | 30 | 1 | 30
7 | Activity 7 | 6 | 100 | 3 | 160
To fill in the Activity Table, please do the following:
1. Give a description for each activity. Please do not change the activity names.
2. Give the duration (in unit time) for each activity and the activity cost.
3. If you are solving the Time-Cost Tradeoff option, then you will also need to give the crash durations and crash costs for each activity.
4. Click Continue to go to the Precedence Matrix.
You can See Example for help, or View Network to refer to your previously drawn network.
Continue
End
See Example
View Network
Activity Table

## Precedence Matrix Sheet (hidden)
| s | 1 | 2 | 3 | 4 | 5 | 6 | 7 | t
s |  | 1 |  |  | 1
1 |  |  | 1 | 1
2 | [5 empty] | 1
3 | [6 empty] | 1
4 | [7 empty] | 1
5 | [8 empty] | 1
6 | [8 empty] | 1
7 | [8 empty] | 1
t
To fill in the Precedence Matrix, please do the following:
For the CPM option:
Looking at event number in each row, enter the Activity Name (number) which connects it directly to the event number in each column.
For the Time-Cost Tradeoff option:
Looking at the activity number in each row, enter a 1 for every cell whose column activity number is directly connected.
Click Solve to see the solution. (You can See Example for help, or View Network to refer to your previously drawn network.)
Solve
End
See Example
View Network
Precedence Matrix

## Report Sheet (hidden)
Event | Early Time | Late Time | Activity | Free Float | Total Float | Critical Path? | Projec Duration
Project Cost
This Report shows the following:
1. The Early Time and Late Time for each event.
2. The Free Float and Total Float of each activity.
3. Which activities are on the Critical Path.
You can View Network to see the highlighted Critical Path.
End
View Network
Final Report

## TradeOff (hidden)
Desired Project Duration | Achieved Project Duration | Project Cost
12 | 12 | 490
11 | 11 | 530
10 | 10 | 570
9 | 9 | 640
8 | 8 | 710
This Report shows the following:
The Desired Project Duration, Achieved Project Duration, and Project Cost for each time crashing scenario.
End
Time Cost Tradeoff Results

## Optimize (hidden)
| Decision Variables |  |  | Constraints | [6 empty] | Objective Function
Activity | Start Time per Activity | Crash Time per Activity | <= | (ai - bi) | u(t) - u(s) | <= | Project Duration | u(j) | >= | u(i) + (ai - Bi) | Min | Project Cost
s | 0 | 0 |  | 0 | 7 |  | 7 | 0 |  | 0 | 0 | 290
1 | 0 | 2 |  | 2 |  |  |  | 0 |  | 0 | 70
2 | 4 | 1 |  | 1 |  |  |  | 4 |  | 4 | 50
3 | 3 | 0 |  | 0 |  |  |  | 3 |  | 4 | 0
4 | 0 | 0 |  | 0 |  |  |  | 5 |  | 5 | 0
5 | 5 | 2 |  | 2 |  |  |  | 6 |  | 6 | 40
6 | 6 | 0 |  | 0 |  |  |  | 2 |  | 2 | 0
7 | 2 | 1 |  | 3 |  |  |  | 7 |  | 7 | 20
t | 7 | [6 empty] | 7 |  | 7
[8 empty] | 7 |  | 7
End
Crashing LP Model

## Example (hidden)
CPM Network
Time-Cost Tradeoff Network
Activity Table
|  | Activity Name | Description | Normal Duration | Normal Cost | Crash Duration | Crash Cost
|  | 1 | Activity 1 | 6 | 100 | 4 | 240
|  | 2 | Activity 2 | 2 | 100 | 1 | 150
|  | 3 | Activity 3 | 3 | 30 | 3 | 30
|  | 4 | Activity 4 | 2 | 30 | 2 | 30
|  | 5 | Activity 5 | 4 | 100 | 2 | 180
|  | 6 | Activity 6 | 1 | 30 | 1 | 30
|  | 7 | Activity 7 | 6 | 100 | 3 | 160
Precedence Matrix: CPM
| 1 | 2 | 3 | 4 | 5 | 6
1 |  | 1 |  |  | 4
2 |  |  | 3 | 2
3 | [5 empty] | 6
4 | [5 empty] | 5
5 | [5 empty] | 7
6
Precedence Matrix: Time Cost Tradeoff
| s | 1 | 2 | 3 | 4 | 5 | 6 | 7 | t
s |  | 1 |  |  | 1
1 |  |  | 1 | 1
2 | [5 empty] | 1
3 | [6 empty] | 1
4 | [7 empty] | 1
5 | [8 empty] | 1
6 | [8 empty] | 1
7 | [8 empty] | 1
t
Return to Network Sheet
Example
Return to Activity Table
Return to Precedence Matrix
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2

## Deleted (hidden)
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
1
2
4
5
4
6
3
7
6
5
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
6
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
5
6
7
4
3
2
t
s
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2
1
2
3
3
5
5
5
4
6
8
6
4
2