## Codes
Reason Code | Title | Example
0 | No time added. | For use in the Time Reason code box only when time is not an issue on the Change Order.
1 | Error in Plans, Specifications, Design | Use 1a..1n as it applies to the change order
1a | Other-describe in narrative on supporting data sheet | None of the categories below fit the change, describe the reason in the narrative area on the supporting data sheet.
1b | Design solution concept in error | · Staging conflicts
· Unbuildable as shown on plans
· Overlay reduced bridge clearance
1c | Required work missing in plans and specifications | · Fuel escalation
· Mailbox supports
· Subexcavation
· Additional preparation, painting and repair
1d | Dimensions or locations missing or in error on plans | · Ordinary high water elevation in error
1e | Specific item of work improperly specified, correction required | · Wrong type of manhole
· Wrong type of inlet
1f | Quantity estimate grossly inaccurate | · Estimate is 140 units, build 14,000 units
· Four (4) bridge beams, not eight (8)
1g | Required change to quantity units or measurement | · Change from unit to LS
· Change from M3 to M2
1h | Specific product or material impossible to obtain | · Manufacturer out of business.
· Steel item from outside of US and no FHWA waiver.
· Don’t confuse this with a Contractor choice or request.
1i | Specified product or material not acceptable | · During construction it is determined that the product or material specified does not work as intended and needs to be changed
1j | Material source/disposal source missing or not properly addressed in plans and specifications | · Mandatory disposal site of insufficient capacity.
1k | Hazardous materials issues not properly addressed | · Undiscovered during project development, required disposal documentation omitted, changes to work or payment.
· Steel slag improperly allowed as embankment material.
1l | Discrepancies between permit requirements and contract plans and specifications | · Clarifying in-water work periods, work allowed, restrictions, etc.
· Pile driving in turtle area.
· Noise not properly addressed in Specs.
· Nesting restrictions not properly specified.
1m | Design calculation error requires change to specified work | · Pipe sizing incorrect due to design calculation error.
· Road approach or DW grades improperly specified.
1n | Design solution concept not within accepted ODOT design standards | · Superelevation correction
· But not in error or it would be a 1b
2 | New requirements by regulatory agencies after contract advertised | · NMFS Restrictions, environmental changes
3 | Updates on wages (not under control of ODOT) | · BOLI Rates change.
4 | Scope changes either increasing or decreasing work from original design intent
Use 4a … 4c as it applies to the change order
4a | Required to complete the project | · Subexcavation
4b | Discretionary, added at request of Region. | · Additional overlay length
4c | Discretionary, paid for by others
5 | Differing site conditions / Latent changed conditions | · Unknown ancient cemetery
6 | Cost reduction proposal
7 | Clarification of specifications or design/include new or updated specifications | · Seeding mixures
8 | ODOT construction engineering error | Use 8a or 8b as it applies to the change order
8a | Other (describe on Supporting Data Sheet)
8b | Correct PM caused environmental problem
9 | Modifications to correct or accept deficiencies in Contractor's workmanship or materials
Use 9a or 9b as it applies to the change order
9a | Other (describe on Supporting Data Sheet)
9b | Correct Contractor caused environmental problem
10 | Added or Extra Work, that was not antificipated, needed to complete the project within the original design intent.
11 | Added or Extra Work, shown as an anticipated item, needed to complete the project within the original design intent.
12 | Delays by weather or parties not under control of Contractor | · Weather meeting ODOT’s reasonably predictable weather criteria
13 | Delays or conflicts associated with utilities | · Late utility relocations
Work Types:
A | None of the below
B | Bridge
C | Roadway
D | Geotech
E | Environmental
F | Traffic
G | Staging
H | Drainage
I | Material Sources/Disposal Sites
J | Hazmat
K | Mobility

## 01
CONTRACT CHANGE ORDER (Page 1)
NOTICE: THIS FORM MUST BE TYPEWRITTEN
PROJECT NAME (SECTION) | [13 empty] | REGION |  | CONTRACT NO.
TPN Example
HIGHWAY | [7 empty] | PROJECT MANAGER |  |  |  | ODOT LIAISON (if PM is non-ODOT) |  |  |  | F.A. PROJECT NO.
CONTRACTOR NAME AND ADDRESS | [7 empty] | CONSULTANT OR LOCAL AGENCY PM NAME AND ADDRESS | [7 empty] | CHANGE ORDER #
THIS CONTRACT IS HEREBY MODIFIED AS FOLLOWS (DESCRIPTION AND LOCATION OF WORK COVERED BY THIS ORDER):
Allow Third Party Neutral (TPN), establish select process, procedures for use of TPN, and method of payment to TPN.
SPECIFICATIONS AND PROVISIONS - THE WORK TO BE DONE UNDER THIS ORDER IS TO BE PERFORMED, MEASURED, AND PAID FOR IN ACCORDANCE WITH THE TERMS FOR THE ABOVE CONTRACT EXCEPT AS MODIFIED AS FOLLOWS -
See Attachment A.
PAY ITEM | Sub Job | DESCRIPTION | [8 empty] | EST. QTY. |  | UNIT | UNIT PRICE |  | AMOUNT
4###a |  | Amend DB 199 to allow a TPN
4###b |  | Payment for TPN | [8 empty] | 75000 |  | dollar | 0.5 |  | 37500
4###c |  | 8% contractor markup | [8 empty] | 75000 |  | dollar | 0.08 |  | 6000
[11 empty] | TOTAL FROM PAGE 2 |  |  |  |  | 0
Additional items listed on attached Page 2
ESTIMATED NET COST EFFECT OF THIS AGREEMENT ON THE CONTRACT: | [11 empty] | INCREASE |  |  |  | 43500
X
DECREASE
CONTRACTOR SIGNATURE
CONTRACTOR SIGNATURE MAKES THIS CONTRACT CHANGE ORDER A SUPPLEMENTAL AGREEMENT
FOR SUPPLEMENTAL AGREEMENTS ONLY: Contractor: Please indicate your agreement by signing, dating and returning the original to the Project Manager. Work shall not begin until you are notified that the agreement has either been approved or that work may commence under advance approval. Your signature further indicates agreement that payments in accordance with the agreement constitute full and complete compensation for all costs, both direct and indirect, arising out of the described work covered by this agreement, and releases and discharges the State from other costs except as provided herein.
CONTRACTOR SIGNATURE | [6 empty] | DATE |  | ODOT PM or LAL |  |  |  | RECOMMENDED |  | APPROVED |  | DATE
Print | [8 empty] | Print
Sign | [8 empty] | Sign
RECOMMENDED BY LOCAL AGENCY | [6 empty] | DATE |  | AREA MANAGER: |  | NOTED |  | RECOMMENDED |  | APPROVED |  | DATE
Print | [8 empty] | Print
Sign | [8 empty] | Sign
RECOMMENDED BY CONSULTANT AGENCY PM | [6 empty] | DATE |  | CONSTRUCTION SECTION: |  |  |  | NOTED |  | APPROVED |  | DATE
Print
Sign
ODOT (Internal): After obtaining Contractor's signature, the Project Manager signs and submits the original through the Area Manager to Construction Section ODOT (Outsourced): After obtaining Contractor's signature, the Project Manager submits original to ODOT CPM or Local Agency Liaison, as appropriate, who then submits through the Area Manager to Construction. All Projects: Construction will distribute fully signed copies to PM, CPM, Contractor, and others as appropriate.
734-1169 (6-2008) | [16 empty] | Contractor: Sign all pages.
CONTRACT CHANGE ORDER (Page 2)
PROJECT NAME (SECTION) | [10 empty] | CONTRACT NO. |  |  | CONTINUATION OF CCO NO.:
TPN Example | [10 empty] | 0 |  |  |  |  | 0
PAY ITEM | Sub Job | DESCRIPTION | [8 empty] | EST. QTY. |  | UNIT | UNIT PRICE |  | AMOUNT
PAGE 2 TOTAL | [15 empty] | 0
CONTRACTOR SIGNATURE | [6 empty] | DATE |  | PROJECT MANAGER OR LOCAL AGENCY LIAISON SIGNATURE | [7 empty] | DATE
734-1169 (6-2008)
WORK OR CHANGE ORDER SUPPORTING DATA (Page 1)
PROJECT NAME (SECTION) | [15 empty] | CONTRACT NO.
TPN Example | [15 empty] | 0
HIGHWAY | [11 empty] | F.A. PROJECT NO.
0 | [11 empty] | 0
NET EFFECT OF ORDER ON PROJECT | [5 empty] | AMOUNT |  |  | CONSTRUCTION AUTH. |  |  | EST. PROJECT COST W/ORDER |  |  |  | OVERRUN %
[5 empty] | 43500 | [10 empty] | #DIV/0! | #DIV/0!
ESTIMATED STARTING DATE* |  |  |  | OR | DATE WORK WAS STARTED* |  |  |  | WORK/CHANGE IS MAJOR? |  |  |  | TO ACCOMPANY (ORDER TYPE & NUMBER)
[13 empty] | CCO |  |  | 0
PREPARED BY | [5 empty] | DATE |  |  | REVIEWED BY AREA MANAGER | [7 empty] | DATE
WORK OR CHANGE HAS BEEN DISCUSSED WITH
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
PRIOR APPROVAL TO PROCEED WITH THE WORK OR CHANGE HAS BEEN OBTAINED FROM*
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
WORK OR CHANGE HAS BEEN DISCUSSED WITH FHWA
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
FHWA TENTATIVE APPROVAL OBTAINED FROM
Name |  |  |  |  | Title |  |  |  |  | Name |  |  | Title |  |  | DATE
BY
FOR CONTRACT CHANGE ORDERS THAT CHANGE A CONTRACT PRICE OR DETERMINE A NEW PRICE --
PM's COST ESTIMATE IS ATTACHED:
ADDITIONAL INFORMATION THAT IS NOT INCLUDED ON ORDER (Additional Description; Who requested; Why necessary; Why cost is not a contractor responsibility; Parties other than State or FHWA that have agreed to share the costs; Emergency work prior to approval; Estimate effect on project time; Significant discussions; References to supporting and/or attached documents, including cost estimates for "Extra Work Orders" and "Force Orders"; Why contractor refuses to sign). List all previously approved overruns.
734-1882 (6-2008) | [16 empty] | *EXCEPT IN EMERGENCY SITUATIONS, THE WORK OR CHANGE MAY NOT PROCEED WITHOUT PROPER PRIOR APPROVAL(S)
WORK OR CHANGE ORDER SUPPORTING DATA (Page 2) REASON CODES
PROJECT NAME (SECTION) | [10 empty] | CONTRACT NO. |  |  | TO ACCOMPANY (ORDER TYPE & NO.)
TPN Example | [10 empty] | 0 |  |  | CCO |  | 0
PAY ITEM | REASON CODE (1-13) | TIME CODE (0-13) | WORK TYPE (A-K) | DESIGN (E or I) | PM (E or I) | DESCRIPTION |  |  |  |  | EST. QTY. |  | UNIT | UNIT PRICE |  | AMOUNT
4###a | 7 | 0 | A |  |  | Amend DB 199 to allow a TPN
4###b | 7 | 0 | A |  |  | Payment for TPN |  |  |  |  | 75000 |  | dollar | 0.5 |  | 37500
4###c | 7 | 0 | A |  |  | 8% contractor markup |  |  |  |  | 75000 |  | dollar | 0.08 |  | 6000
TOTAL | [15 empty] | 43500
734-2616 (6-2008)
Note on S7: If you have any comments regarding this form, please contact Lori Butler at 503.986.3007 or by e-mail (lorraine.e.butler @ odot.state.or.us)
Note on S119: The box to the left is a text box. You must click in the box to use it (you cannot tab into it). This allows the entire box to be filled with text (and printed). Tab can be created by using Ctrl+Tab. Blank lines can be create by using Ctrl+Enter.
Note on S137: The Pay Item, Description, Est. Qty, Unit, Unit Price, and Amount will come from the change order form. Only the Reason Code area needs to be completed on this form
Note on T35: This box should be signed by the ODOT representative for the project (Project Manager, Consultant Project Manager, Local Agency Liaison)
Note on S17: Any attachments listed in the Description and Specification description areas are part of the Change Order and must be labeled with Contract No, change order number, and attachment number.
Note on T55: Only need to include this page if there are items listed.